## Discovery Analysis
Type | Tests |  | Test Available | Test that Meets description | Initail Comments | Follow up Analysis | Task in Jira
Entitlements | Sub-type | Scenario
| Dashboard Entitlement | All Users for client presented with Dashboard | No |  | Not on the black list: gets new murano Discussed technique with Falgu: Needs a test Two or three tests needed here. With, without, withbut on blacklist Notes: The Team 1 Murano Dashboard is Very Angular. So, we should only have to look in the code of the page to see that they either got a very angualr page or one that is not like that at all | With a set of users known to have UK Murano Payment entitlement 1) As a UK Murano Entitled User, Login and Navigate to Home Page ( dashboard ) * if user lands on Angular Team 1 page : PASS * If user lands on a page thats not Angular Team 1 Page: FAIL ( would be eC page ) | MPAY-2502
|  | New user added | No |  | have a clie with a user. Add a new user. They get new dashboard | 2) As a User without any UK Murano Payment entitlement, Login and nav to Home page * If eConnect Home page: PASS * If Team 1 Dashboard well that would be a FAIL It seems like any other than eConnect should be considered a FAIL | MPAY-2503
|  | All Users for client have dashboard removed | No |  | Black list approach. If on then old dashboard ( ec) I don't want to see dashboard. We ALL want the old dashboard | 3) As a user or with a SET of users all UK Murano Entitled, But in this case, they are ON THE BLACK LIST * if user lands on Angular Team 1 page : FAIL * If user lands on a page thats not Angular Team 1 Page: PASS ( would be eC page ) | MPAY-2504
| Account View | Accounts Visible on initial set up | No |  | ON Dashboard. They can see acct and cur bal Acct their entitled to… Entitlement is eC ( acct reporting ) How do we automate econnect setting entitlements ??? Notes: We will have to do a little magic ahead of time in setting up this test. I don't remember the exact approach, but.... We need acocunt on FC that we can call to and add to a user Either by scripting or by adding through some I"m going to layout the eC steps that I think we need to automate and see what we all thinks | We are either going to set this up by scripting…. Or do by hand. Here are the basics we would do by scripting Protractor query account balances Create the user Login as the User Compare the balances with the values queried just recently | MPAY-2505
|  | Account(s) removed from view / access | No |  | If they loose entitlement to see an acct, then they can't see it Log on as a specific user. recored a list of the accounts available This means these accounts are entitled to be seen/accessed ( funding accounts ) Take entitlement away on an account Reevaluate the list of available accounts. It must decrease the same as entitlement taken away. | Setup a test user with a specific set of accounts login as that user and verify that specific accounts are displayed on the dashboard Then check from the make payment funding account dropdown. Now via scripting at db or automat the eC, and take away access to one, many , or all of these accounts. No review the accounts on Dashboard and from funding Dropdown for account that are NO LONGER Visable. | Mpay-2506
|  | Account(s) added to view / access | No |  | Get added , then they see new acct. Execute the corollary to the test above. Add to the list of accounts available. | Log in as a specific Test user. Revew available accounts in the dashboard Review accounts in the payments funding account dropdown. Make additional accounts available to this user. What is the term , assign them ? Now perform the same account list check The proper list of accounts is visible : PASS Incorrect list of accounts is visible : FAIL | MPAY-2507
| Account / Limit | User Account Limits | Yes | Cumulative Limits Section 30 | per xaction, cumulavtive limit per day at user level Client per xaction , client limit per day Cumulative Notes: These are FC live payments that will go alll the way They need to be unique values per FC suspecision rules Other Comment: But this test is not as exhautive as the manual test should allow a payment that does not exceed the daily limit for the client should allow a payment that exactly reaches the daily limit for the client should not allow a payment that exceeds the daily limit for the client
|  | User Account Limit Exceeds Faster Payment Threshold | No |  | Client Limit and User Limit have to be set higher than the 100K FPS limit
|  | User Access to Dormant Account | No |  | Flexcube specific: Have to entitle to an acct that is in dormant status ( in FC ) Dorment acct WILL NOT show up in the Funding acct list !!! Check that they have entitielent to this acct, then check the FE if acct is dormant and shows in app, that is a FAIL WE dont' want to see it.
|  | User Access to Closed Account | No |  | Flexcube specific: Have to entitle to an acct that is in closed status ( in FC ) closed acct WILL NOT show up in the Funding acct list !!! Check that they have entitielent to this acct, then check the FE if acct is closed and shows in app, that is a FAIL WE dont' want to see it.
|  | User Access to USD Account | No |  | Entitled to acct. Can see in UK Dashboard. WILL NOT see in funding acct drop list
Faster Payments | FPS – No Exception | Immediate Faster Payment (Pre-Cut Off) on Account with no exceptions | No |  | Faster pay before cutoff actually goes ALL The Way to FC We want to see the FC output. Hmmmm Selenium Webdriver Java Notes: Across Several of these tests, Dollar / Pound amounts need to all be different otherwise it get's flagged as suspicious behaviour
|  | Account with no exceptions, future dated [NOTE - covers scenario for post cut-off) | No |  | After cutoff. Get the next bus day as the payment date! And we want to see in _FC_ that it get's processed at 6:00 am +300ms
|  | Account with no exceptions, future dated [NOTE - covers scenario for bank holidays) | No |  | Bank Holidays. Friday night submission. Sat, Sun, MonHOliday. Payment date is set for Tuesday. Notes: This is not an easy test to Automate because So much time elapses between start and check
| FPS – Overrides | Account with No Debits, soft hold | No |  | NO DEBITS is a FC concept that stops smooth flowthrough…. Pay gets into FC and an FC user has to interact to push payment through FC Approve or reject are the operator's options in FC Pmt Request gets into FC in Payment Pending Auth Approved: would not show any indication. All would be well with the pay workflow w.r.t the mpayments user Rejected: Payment would still say "SENT", but would FAIL and user shojuld be getting a phone call from FC Administrator Notes: IN the Rejection payment audit report would represent this as Success, but would not report a debit to the account ! What does number of payments show??? What does $$$ value shoe ??? We will need to see FC screens
|  | Fraud threshold exceeded (Txn exceeds £20,000) | No |  | This is none of the other conceptual limits built in our system. This is an arbitrary thing the bank does on a whim . Value set in FC. Hit this limit and you go into pending Auth Queue. ---- Just like the previous story there are no indications to the user in the murano payments app that this has happened Will hapend TO ALL Account types regardless if the hit the limit. Notes: We will need to see the FC Screens
|  | FPS Limit Exceeded | No |  | Currently understood
|  | Account overdrawn with no facility | No |  | Pending Auth, Accept Reject. Like prev two, the user will not see. Notes: We will need to see the FC Screens
| FPS – Errors | Account with No Debits hard hold | No |  | Immediate rejection. No indication in Murano payments App FC will never acknowledge/ record the payment . Its like it never happened. But, we publish an end point that FC can grab and write to the DB about this failure Email is also gened to the UK Payment operations people Notes: There is NO FC Screen to SEE !!
|  | Account closed - Payment from (payment made mid closure) | No |  | Special condition between today and tomorrow This morning account is open. Noon account is closed Afternoon a payment is made against this account. It will go to FC ===== And Susan has to check what happens We think it will be Pending Auth then reject
|  | Account closed - Payment to | No |  | This is the receiving end who has a closed account The payment would go through as everthing is valid pay sits at the other end of unposted xactions No indication to the user on our end. Notes: Payment audit will show every thing as green User dashboard will show the initial debit and then show the credit when it's made. Murano payment app shows NOTHING We don't know at this time how we could test this. ON the BACk Burner.
|  | Account dormant - Payment From (payment made mid dormant) | No |  | Behavior will be the same as payment made mid closure
|  | Account invalid | No |  | This is a new Client/user or other Client/user management process that we do with scripting, where we might have entered the wrong account number on the funding account
|  | Account not GBP | No |  | if accidentally if user is entitled to a US $ account, The expectation is that the accound WILL NOT SHOW in the Funding account list dropdown
Fraud Management | Authentication Testing | User makes payment with successful code entry--CTV and TTV | YES | OOBA_Payment CTV Flow | Currently in progress with TTV Voice could be a hurdle to get over : )
|  | User attempts to enter code incorrectly 3 times and is frozen | No |  | 1 fail look at audit and see one fail : user status active 2 fail look at audit and see two fail : user status active 3 fail look at audit and see three fail : user status frozen, but session is left active. Logout and relogin MUST fail =============== Another test Same Test workflow, 4th attempt successful ( or 5th, 6th) Audit report shows user Status Active. Notes: you can see a frozen user in the audit report Initiate auth success Verify Auth FAIL Three times for TTV Addtional Comment: Fail three times and you are in fact FROZEN. If you logout, you're done !!!... Our workflow does not kick you out eventhough you are frozen. It keeps you active. So frozen and active can fail three mor times. At that time, the session is INVALIDATED which kicks you out.
|  | User attempts to enter code incorrectly 6 times and is Logged out | No |  | Same as above but on the 6th fail, the audit report shows The verify Auth has a different wroding
| User Monitoring/Tealeaf | Login visible through Monitoring
Account Summary and Navigation Visible through Monitoring
Create recipient visible through monitoring
Create payment visible through monitoring
Logoff visible through Monitoring
Low Risk Payment Captured
Medium Risk Payment Captured
High Risk Payment Captured

## Plan to meet Gap
Type | Tests | 0 | Test Available | Test that Meets description
Entitlements | Sub-type | Scenario
| Dashboard Entitlement | All Users for client presented with Dashboard | No
|  | New user added | No
|  | All Users for client have dashboard removed | No
| Account View | Accounts Visible on initial set up | No
|  | Account(s) removed from view / access | No
|  | Account(s) added to view / access | No
| Account / Limit | User Account Limits | Yes | Cumulative Limits Section 30
|  | User Account Limit Exceeds Faster Payment Threshold | No
|  | User Access to Dormant Account | No
|  | User Access to Closed Account | No
|  | User Access to USD Account | No
Faster Payments | FPS – No Exception | Immediate Faster Payment (Pre-Cut Off) on Account with no exceptions | No
|  | Account with no exceptions, future dated [NOTE - covers scenario for post cut-off) | No
|  | Account with no exceptions, future dated [NOTE - covers scenario for bank holidays) | No
| FPS – Overrides | Account with No Debits, soft hold | No
|  | Fraud threshold exceeded (Txn exceeds £20,000) | No
|  | FPS Limit Exceeded | No
|  | Account overdrawn with no facility | No
| FPS – Errors | Account with No Debits hard hold | No
|  | Account closed - Payment from (payment made mid closure) | No
|  | Account closed - Payment to | No
|  | Account dormant - Payment From (payment made mid dormant) | No
|  | Account invalid | No
|  | Account not GBP | No
Fraud Management | Authentication Testing | User makes payment with successful code entry--CTV and TTV | YES | OOBA_Payment CTV Flow
|  | User attempts to enter code incorrectly 3 times and is frozen | No
|  | User attempts to enter code incorrectly 6 times and is Logged out | No
| User Monitoring/Tealeaf | Login visible through Monitoring
Account Summary and Navigation Visible through Monitoring
Create recipient visible through monitoring
Create payment visible through monitoring
Logoff visible through Monitoring
Low Risk Payment Captured
Medium Risk Payment Captured
High Risk Payment Captured