## Discovery Analysis
Type | Tests |  | Test Available | Test that Meets description | Initail Comments | Follow up Analysis | Task in Jira
Entitlements | Sub-type | Scenario
| Dashboard Entitlement | All Users for client presented with Dashboard | No |  | Not on the black list: gets new murano Discussed technique with Falgu: Needs a test Two or three tests needed here. With, without, withbut on blacklist Notes: The Team 1 Murano Dashboard is Very Angular. So, we should only have to look in the code of the page to see that they either got a very angualr page or one that is not like that at all | With a set of users known to have UK Murano Payment entitlement 1) As a UK Murano Entitled User, Login and Navigate to Home Page ( dashboard ) * if user lands on Angular Team 1 page : PASS * If user lands on a page thats not Angular Team 1 Page: FAIL ( would be eC page ) | MPAY-2502
|  | New user added | No |  | have a clie with a user. Add a new user. They get new dashboard | 2) As a User without any UK Murano Payment entitlement, Login and nav to Home page * If eConnect Home page: PASS * If Team 1 Dashboard well that would be a FAIL It seems like any other than eConnect should be considered a FAIL | MPAY-2503
|  | All Users for client have dashboard removed | No |  | Black list approach. If on then old dashboard ( ec) I don't want to see dashboard. We ALL want the old dashboard | 3) As a user or with a SET of users all UK Murano Entitled, But in this case, they are ON THE BLACK LIST * if user lands on Angular Team 1 page : FAIL * If user lands on a page thats not Angular Team 1 Page: PASS ( would be eC page ) | MPAY-2504
| Account View | Accounts Visible on initial set up | No |  | ON Dashboard. They can see acct and cur bal Acct their entitled to… Entitlement is eC ( acct reporting ) How do we automate econnect setting entitlements ??? Notes: We will have to do a little magic ahead of time in setting up this test. I don't remember the exact approach, but.... We need acocunt on FC that we can call to and add to a user Either by scripting or by adding through some I"m going to layout the eC steps that I think we need to automate and see what we all thinks | ON Dashboard. They can see accounts and cur balance accounts their entitled to… How do we automate eConnect setting entitlements ??? Test: We are either going to set this up by scripting…. Or do by hand. Via Scripting: Identify all the new users account particulars Names, Numbers, Balances Create the user - This must be a NEW FEATURE. Currently MurPayments doesn't have Create a New User Feature ( so external for now ) Login as the User Compare the balances with the values queried just recently Notes & Questions: What in this test is internal to automating a Murano Payments test, and what is external. I dont' know how much access we have to eConnect and eC account names and balances. but we would need this stuff Also, it might not be eC-Accounts, it might be more to the point that these are FC accounts. (seems most likely) | MPAY-2505
|  | Account(s) removed from view / access | No |  | If they loose entitlement to see an acct, then they can't see it Log on as a specific user. recored a list of the accounts available This means these accounts are entitled to be seen/accessed ( funding accounts ) Take entitlement away on an account Reevaluate the list of available accounts. It must decrease the same as entitlement taken away. | Setup a test user with a specific set of accounts login as that user and verify that specific accounts are displayed on the dashboard Then check from the make payment funding account dropdown. Now via scripting at db or automat the eC, and take away access to one, many , or all of these accounts. No review the accounts on Dashboard and from funding Dropdown for account that are NO LONGER Visable. | Mpay-2506
|  | Account(s) added to view / access | No |  | Get added , then they see new acct. Execute the corollary to the test above. Add to the list of accounts available. | Log in as a specific Test user. Revew available accounts in the dashboard Review accounts in the payments funding account dropdown. Make additional accounts available to this user. What is the term , assign them ? Now perform the same account list check The proper list of accounts is visible : PASS Incorrect list of accounts is visible : FAIL | MPAY-2507
| Account / Limit | User Account Limits | Yes | Cumulative Limits Section 30 | per xaction, cumulavtive limit per day at user level Client per xaction , client limit per day Cumulative Notes: These are FC live payments that will go alll the way They need to be unique values per FC suspecision rules Other Comment: But this test is not as exhautive as the manual test should allow a payment that does not exceed the daily limit for the client should allow a payment that exactly reaches the daily limit for the client should not allow a payment that exceeds the daily limit for the client | User Per Trans action Cumulaitve limt per day at user level Client per transaction Client limit per day ( Single or multiple ) Here are the values and settings to set this sequence of test up properly. Names are not going to be exactly correct, but it should be obvious within minutes of reading all of this. This setup comes out of MPAY-1538. I’ve rearranged the placement of the limits in a (slightly) more logical order Moved 51K up under 25K Test setup JavaScript Protractor file paymentServiceScripts.js or DBConnectionManager.js Set FPS System Limit : Set a users Max transaction limit ( diff users can have diff Limits ) PAYMENT.PAYMENT_TYPE.MAX_SYS_TRAN_AMT $100000 WHERE INTERNAL_NAME == PAYMENT_FPS Set a Max for a users per Transaction amount ENTITLEMENT.USER_ENTITLEMENT.MAX_TRAN_AMT == $25000 Set a Max Limit on individual Client Transaction( diff users can have diff limits ) This value limits a clients exposure if the user limit is miss configured ENTITLEMENT.CLIENT_LIMIT.MAX_PER_TRAN_AMT == $51000 Set a Max for a users accumulation for a day ENTITLEMENT.USER_ENTITLEMENT.MX_DAILY_CUMULATIVE_LIMIT == $55000 | MPAY-2537 for mpay-2538 mpay-2539 mpay-2540 mpay-2541
Set a Max for a Clients accumulation for a day ENTITLEMENT.CLIENT_LIMIT.MAX_DAILY_TRAN_AMT == $80000 These queries are going to have to be corrected and be more UserID or Client ID specific. Previous testing simply set the same value on every db row. I need to focus on one specific user row // User Per TransAction Amount: Testing 25K update USER_ENTITLEMENT SET MAX_TRAN_AMT = 25000 WHERE function_name like 'CREATE_%' and user_id in (select user_id from USER_ENTITLEMENT where MAX_TRAN_AMT != 25000 ); commit ;
// User Cumulative Limit per day: Testing 55K update USER_ENTITLEMENT SET MAX_DAILY_CUMULATIVE_LIMIT = 55000 WHERE function_name like 'CREATE_%' and user_id in (select user_id from USER_ENTITLEMENT where MAX_DAILY_CUMULATIVE_LIMIT != 55000); commit;
// Client Per Transaction Amount: Testing 51K update CLIENT_LIMIT SET MAX_PER_TRAN_AMT = 51000 WHERE function_name like 'CREATE_%' and client_id in (select client_id from CLIENT_LIMIT where MAX_PER_TRAN_AMT != 51000); commit;
// Client Cumulaitve Limit Per Day: Testing 80K update CLIENT_LIMIT SET MAX_DAILY_TRAN_AMT = 80000 WHERE function_name like 'CREATE_%' and client_id in (select client_id from CLIENT_LIMIT where MAX_DAILY_TRAN_AMT != 80000) ; commit;
TESTING FPS System Limits : in the following order Logon as FPS Client User #1 -1) Create payment 100,000.01 Should FAIL With all limits set low MAX_FPS still not achievable -2) Create a payment of 25,000.01 Should FAIL 0.01 greater than User Max Tran -3) Create a payment of 25K should PASS At Lim of User Max Tran & 25K into User Cumulative Lim -4) Create a payment of 25,000.01 should FAIL 0.01 greater than User Max Tran -5) Create a payment of 25K Should PASS At Lim of User Max Tran & 50K into User Cumulative Lim -6) Create a payment of 5,000.1 Should FaIL 0.01 greater than User Cumulative Lim -7) Create a payment of 5K Should PASS Now Matches the User Cumulative Limt or 55K -8) Create a payment of 0.01 Should FAIL 0.01 greater than the User Cumulative Limit or 55K
Login as FPS Client User #2 . -9) Create payment of 25,000.01 Should FAIL 0.01 greater than Client Cumulative limit -10) Create payment of 25K Should PASS Matches the Client Cumulative Limit 80K -11) Create payment of 0.01 Should FAIL 0.01 greater than Client Cumulative limit 80K Modify User Transaction Limit Value from 25K to 125K Remove USER Per Transaction & cumulative Limits Login as new Client User #3
cont.. -12) Create a payment of 51,000.01 Should FAIL 0.01 greater than Client Max per Transaction -13) Create a payment of 51K Should PASS At Lim of Cli Per trans 51K Modify Client Per Transaction limit 51K to 151K . -14) Create a payment of 55,000.01 Should FAIL At Limi of User Cumulative Limit 55K -15) Create a payment of 55K Should PASS Matches Limit of user Cumulative Limit 55K Modify User Cumulative Limit 55K to 155K Login as a new user
|  | User Account Limit Exceeds Faster Payment Threshold | No |  | Client Limit and User Limit have to be set higher than the 100K FPS limit |  | mpay-2542
|  | User Access to Dormant Account | No |  | Flexcube specific: Have to entitle to an acct that is in dormant status ( in FC ) Dorment acct WILL NOT show up in the Funding acct list !!! Check that they have entitielent to this acct, then check the FE if acct is dormant and shows in app, that is a FAIL WE dont' want to see it. | To Test: Do this backward from how Susan spoke of it and how I wrote it. Start with an account I have entitlement & access to and can see. Logout as this user. Clear the cache and history Then have FC make the account Entitled and DORMANT. Login as this user If the Account is GONE: PASS If the account is visible : FAIL | mpay-2543
|  | User Access to Closed Account | No |  | Flexcube specific: Have to entitle to an acct that is in closed status ( in FC ) closed acct WILL NOT show up in the Funding acct list !!! Check that they have entitielent to this acct, then check the FE if acct is closed and shows in app, that is a FAIL WE dont' want to see it. | To Test: Open with a user who has entitlement to a specific account Make a payment with said account : PASS Programmatically change the status of the account Re open the make payment page If the funding account is there : FAIL If the funding account is missing : PASS | mpay-2544
|  | User Access to USD Account | No |  | Entitled to acct. Can see in UK Dashboard. WILL NOT see in funding acct drop list | To Test: Take a client and user and make sure they can see the account from Dashboard they are entitled to see a USD account Entitle a UK Client User to have access to a USD acocunt They can see the account in the UK Dashboard : PASS Open the Make Payment page. They can See the USD account in the dropdown : FAIL The CANNOT see the USD account in the dropdown : PASS | mpay-2545
Faster Payments | FPS – No Exception | Immediate Faster Payment (Pre-Cut Off) on Account with no exceptions | No |  | Faster pay before cutoff actually goes ALL The Way to FC We want to see the FC output. Hmmmm Selenium Webdriver Java Notes: Across Several of these tests, Dollar / Pound amounts need to all be different otherwise it get's flagged as suspicious behaviour | To Test: Send Faster Payment before cutoff We need to see the FC output. ( I say: Hummmm. selenium web driver. ((I now know this is not as easliy feasible as I had thought. FC is a Web Java APP , not a web page. There jiust is not as much FC automation availability | mpay-2551
|  | Account with no exceptions, future dated [NOTE - covers scenario for post cut-off) | No |  | After cutoff. Get the next bus day as the payment date! And we want to see in _FC_ that it get's processed at 6:00 am +300ms | To Test: Commit a payment after cutoff. Validate the next day as payment. Camp out on the process until 6:00 AM London time/ Payment transitions from Scheduled to Sent : PASS No changes to the payment : FAIL | mpay-2552
|  | Account with no exceptions, future dated [NOTE - covers scenario for bank holidays) | No |  | Bank Holidays. Friday night submission. Sat, Sun, MonHOliday. Payment date is set for Tuesday. Notes: This is not an easy test to Automate because So much time elapses between start and check Most other operations are reasonably instantaenous or within 15 seconds. This test on the other hand takes 3-4 days Most automated testing takes place in the present. It’s a right now concept. Do something to the App. Evaluate the response. but here we a scheduling something that will no trigger for three days. This by common automation standards is not automate-able. this is not easy to automate because of the longer duration than a weekend. Still if we had better management of the Holiday calendar we should be able to manage this. Bank Holidays. Friday night submission. Sat, Sun, MonHOliday. Payment date is set for Tuesday. |  | mpay-2553
| FPS – Overrides | Account with No Debits, soft hold | No |  | NO DEBITS is a FC concept that stops smooth flowthrough…. Pay gets into FC and an FC user has to interact to push payment through FC Approve or reject are the operator's options in FC Pmt Request gets into FC in Payment Pending Auth Approved: would not show any indication. All would be well with the pay workflow w.r.t the mpayments user Rejected: Payment would still say "SENT", but would FAIL and user shojuld be getting a phone call from FC Administrator Notes: IN the Rejection payment audit report would represent this as Success, but would not report a debit to the account ! What does number of payments show??? What does $$$ value shoe ??? We will need to see FC screens |  | mpay-2587
|  | Fraud threshold exceeded (Txn exceeds £20,000) | No |  | This is none of the other conceptual limits built in our system. This is an arbitrary thing the bank does on a whim . Value set in FC. Hit this limit and you go into pending Auth Queue. ---- Just like the previous story there are no indications to the user in the murano payments app that this has happened Will hapend TO ALL Account types regardless if the hit the limit. Notes: We will need to see the FC Screens |  | MPAY-2588
|  | FPS Limit Exceeded | No |  | Currently understood | See MPAY-2542 where this is already explored. Is 2589 necessary ??? | MPAY-2589
|  | Account overdrawn with no facility | No |  | Pending Auth, Accept Reject. Like prev two, the user will not see. Notes: We will need to see the FC Screens |  | MPAY-2590
| FPS – Errors | Account with No Debits hard hold | No |  | Immediate rejection. No indication in Murano payments App FC will never acknowledge/ record the payment . Its like it never happened. But, we publish an end point that FC can grab and write to the DB about this failure Email is also gened to the UK Payment operations people Notes: There is NO FC Screen to SEE !! |  | MPAY-2591
|  | Account closed - Payment from (payment made mid closure) | No |  | Special condition between today and tomorrow This morning account is open. Noon account is closed Afternoon a payment is made against this account. It will go to FC ===== And Susan has to check what happens We think it will be Pending Auth then reject |  | MPAY-2592
|  | Account closed - Payment to | No |  | This is the receiving end who has a closed account The payment would go through as everthing is valid pay sits at the other end of unposted xactions No indication to the user on our end. Notes: Payment audit will show every thing as green User dashboard will show the initial debit and then show the credit when it's made. Murano payment app shows NOTHING We don't know at this time how we could test this. ON the BACk Burner. |  | MPAY-2593
|  | Account dormant - Payment From (payment made mid dormant) | No |  | Behavior will be the same as payment made mid closure |  | MPAY-2594
|  | Account invalid | No |  | This is a new Client/user or other Client/user management process that we do with scripting, where we might have entered the wrong account number on the funding account |  | MPAY-2595
|  | Account not GBP | No |  | if accidentally if user is entitled to a US $ account, The expectation is that the accound WILL NOT SHOW in the Funding account list dropdown |  | MPAY-2596
Fraud Management | Authentication Testing | User makes payment with successful code entry--CTV and TTV | YES | OOBA_Payment CTV Flow | Currently in progress with TTV Voice could be a hurdle to get over : )
|  | User attempts to enter code incorrectly 3 times and is frozen | No |  | 1 fail look at audit and see one fail : user status active 2 fail look at audit and see two fail : user status active 3 fail look at audit and see three fail : user status frozen, but session is left active. Logout and relogin MUST fail =============== Another test Same Test workflow, 4th attempt successful ( or 5th, 6th) Audit report shows user Status Active. Notes: you can see a frozen user in the audit report Initiate auth success Verify Auth FAIL Three times for TTV Addtional Comment: Fail three times and you are in fact FROZEN. If you logout, you're done !!!... Our workflow does not kick you out eventhough you are frozen. It keeps you active. So frozen and active can fail three mor times. At that time, the session is INVALIDATED which kicks you out.
|  | User attempts to enter code incorrectly 6 times and is Logged out | No |  | Same as above but on the 6th fail, the audit report shows The verify Auth has a different wroding
| User Monitoring/Tealeaf | Login visible through Monitoring
Account Summary and Navigation Visible through Monitoring
Create recipient visible through monitoring
Create payment visible through monitoring
Logoff visible through Monitoring
Low Risk Payment Captured
Medium Risk Payment Captured
High Risk Payment Captured

## Plan to meet Gap
Type | Tests | 0 | Test Available | Test that Meets description
Entitlements | Sub-type | Scenario
| Dashboard Entitlement | All Users for client presented with Dashboard | No
|  | New user added | No
|  | All Users for client have dashboard removed | No
| Account View | Accounts Visible on initial set up | No
|  | Account(s) removed from view / access | No
|  | Account(s) added to view / access | No
| Account / Limit | User Account Limits | Yes | Cumulative Limits Section 30
|  | User Account Limit Exceeds Faster Payment Threshold | No
|  | User Access to Dormant Account | No
|  | User Access to Closed Account | No
|  | User Access to USD Account | No
Faster Payments | FPS – No Exception | Immediate Faster Payment (Pre-Cut Off) on Account with no exceptions | No
|  | Account with no exceptions, future dated [NOTE - covers scenario for post cut-off) | No
|  | Account with no exceptions, future dated [NOTE - covers scenario for bank holidays) | No
| FPS – Overrides | Account with No Debits, soft hold | No
|  | Fraud threshold exceeded (Txn exceeds £20,000) | No
|  | FPS Limit Exceeded | No
|  | Account overdrawn with no facility | No
| FPS – Errors | Account with No Debits hard hold | No
|  | Account closed - Payment from (payment made mid closure) | No
|  | Account closed - Payment to | No
|  | Account dormant - Payment From (payment made mid dormant) | No
|  | Account invalid | No
|  | Account not GBP | No
Fraud Management | Authentication Testing | User makes payment with successful code entry--CTV and TTV | YES | OOBA_Payment CTV Flow
|  | User attempts to enter code incorrectly 3 times and is frozen | No
|  | User attempts to enter code incorrectly 6 times and is Logged out | No
| User Monitoring/Tealeaf | Login visible through Monitoring
Account Summary and Navigation Visible through Monitoring
Create recipient visible through monitoring
Create payment visible through monitoring
Logoff visible through Monitoring
Low Risk Payment Captured
Medium Risk Payment Captured
High Risk Payment Captured